## ProductBackLog
Project Name: Parking Automation System Group Members: Ayhan Taşdemir, Yasin Polat, Nazmi Ege Güven, Esin Eda Tan, Selin Sinem Ergül, Hande Betül Esgin
# | Product BackLog
1 | Define project scope and objectives
2 | Conduct research on parking automation systems
3 | Set up the development environment
4 | Create the project structure
5 | Design UI with Figma
6 | Develop main UI components
7 | Create database structure
8 | Integrate software with database
9 | Implement authentication system
10 | Develop real-time parking occupancy tracking
11 | Design digital display system
12 | Integrate Raspberry Pi sensors
13 | Implement license plate recognition system
14 | Establish Power BI for analytics and reporting
15 | Implement API integration
16 | Apply data security measures
17 | Develop parking capacity optimization algorithm
18 | Create mobile app notification system
19 | Implement user authorization and role-based access controls
20 | Establish error logging and alert system
21 | Perform unit testing
22 | Conduct integration testing
23 | Perform UI testing
24 | Final evaluation and system deployment preparation
25 | Prepare project documentation

## Sprint-1
SPRINT-1
STAFF | ACTION | STATUS | PRIORITY | START | FINISH | DURATION (DAYS) | NOTES AND COMMENTS
Product Owner | Define project scope and objectives | Not Started | High | 2025-03-18 | 2025-03-18 | 1 | Initial project planning and goal setting
Product Owner | Conduct research on parking automation systems | Not Started | High | 2025-03-19 | 2025-03-19 | 1 | Gather insights from existing parking systems
Developer & Scrum Master | Set up the development environment | Not Started | High | 2025-03-20 | 2025-03-20 | 1 | Ensure tools are correctly configured
Developer & Scrum Master | Create the project structure | Not Started | Medium | 2025-03-21 | 2025-03-21 | 1 | Define folder structure and project flow
Product Owner & Developer & Scrum Master | Design UI with Figma | Not Started | Medium | 2025-03-22 | 2025-03-22 | 1 | UI design to ensure better user experience
Developer & Scrum Master | Develop main UI components | Not Started | High | 2025-03-23 | 2025-03-25 | 3 | Develop core UI elements like buttons, navigation, etc.
12
BACKLOG
As a customer, I want the team to conduct research on parking automation systems so that the system reflects real-world needs and best practices, and I want the user interface to be designed clearly with Figma so that I can easily navigate the system.
STATUS: Ready to Start
As a user, I want the project scope and objectives to be clearly defined so that I can better understand how the system will help me manage parking operations, and I want the project structure to be created in a scalable way so that the system can grow with future updates.
STATUS: Ready to Start
Dev
Dev
As a developer, I want to set up the development environment so that the implementation process can begin smoothly, and I want to develop the main UI components so that the system becomes functional and interactive.
STATUS: In Progress
PO
Dev

## Sprint-2
SPRINT-2
STAFF | ACTION | STATUS | PRIORITY | START | FINISH | DURATION (DAYS) | NOTES AND COMMENTS
Developer & Scrum Master | Create database structure | Not Started | High | 2025-03-26 | 2025-03-26 | 1 | Create the database for data storage
Developer & Scrum Master | Integrate UI with Firebase | Not Started | Medium | 2025-03-27 | 2025-03-28 | 2 | Establish secure connection with Firebase
Developer & Scrum Master | Implement authentication system | Not Started | High | 2025-03-29 | 2025-04-02 | 5 | Implement a secure login system
Product Owner & Developer & Scrum Master | Develop real-time parking occupancy tracking | Not Started | High | 2025-04-03 | 2025-04-14 | 12 | Tracking parking slot availability in real-time
Developer & Scrum Master | Design digital display system | Not Started | Medium | 2025-04-15 | 2025-04-18 | 4 | Design displays to guide drivers in parking
Developer & Scrum Master | Integrate Raspberry Pi sensors | Not Started | Medium | 2025-04-18 | 2025-04-18 | 1 | Connecting sensors to detect vehicle positions
25
BACKLOG
As a user, I want a database structure to be created, so that the system can manage parking data efficiently.
STATUS: Not Started
As a user, I want the UI to be integrated with Firebase, so that I can experience a responsive and real-time interface.
STATUS: Not Started
Dev
QA
As a user, I want the authentication system to be implemented, so that I can securely log in to the system.
STATUS: Not Started
Dev
Dev

## Sprint-3
SPRINT-3
STAFF | ACTION | STATUS | PRIORITY | START | FINISH | DURATION (DAYS) | NOTES AND COMMENTS
Product Owner & Developer & Scrum Master | Implement license plate recognition system | Not Started | High | 2025-04-19 | 2025-04-28 | 10 | Implement AI-based license plate recognition
Developer & Scrum Master | Establish Power BI for analytics and reporting | Not Started | High | 2025-04-29 | 2025-04-30 | 2 | Power BI integration for performance insights
Developer & Scrum Master | Implement API integration | Not Started | Medium | 2025-05-01 | 2025-05-02 | 2 | API integration for third-party services
Developer & Scrum Master | Apply data security measures | Not Started | High | 2025-05-03 | 2025-05-04 | 2 | Add encryption and security layers
Developer & Scrum Master | Develop parking capacity optimization algorithm | Not Started | High | 2025-05-05 | 2025-05-07 | 3 | Algorithm to improve parking space efficiency
Developer & Scrum Master | Create mobile app notification system | Not Started | Medium | 2025-05-08 | 2025-05-09 | 2 | Alert users for parking space availability
21
BACKLOG
As a developer, I want to implement a license plate recognition system so that the system can automatically identify and register vehicles, and I want to implement API integration so that the system can communicate with third-party services and external modules, and I want to apply data security measures so that user data and system information are protected from threats.
STATUS: Not Started
As a developer, I want to establish Power BI integration for analytics and reporting so that we can gain insights from parking data, and I want to develop a parking capacity optimization algorithm so that parking space usage is maximized efficiently, and I want to create a mobile app notification system so that users can receive timely alerts and important updates.
STATUS: Not Started
Dev
PO
Dev

## Sprint-4
SPRINT-4
STAFF | ACTION | STATUS | PRIORITY | START | FINISH | DURATION (DAYS) | NOTES AND COMMENTS
Developer & Scrum Master | Implement user authorization and role-based access controls | Not Started | Medium | 2025-04-29 | 2025-05-01 | 3 | Ensure users have correct permissions
Developer & Scrum Master | Establish error logging and alert system | Not Started | Medium | 2025-05-02 | 2025-05-03 | 2 | Develop system error tracking & alert
Product Owner & Developer & Scrum Master | Perform unit testing | Not Started | High | 2025-05-04 | 2025-05-06 | 3 | Verify individual unit functions
Developer & Scrum Master | Conduct integration testing | Not Started | Medium | 2025-05-07 | 2025-05-08 | 2 | Ensure systems interact correctly
Developer & Scrum Master | Perform UI testing | Not Started | Medium | 2025-05-09 | 2025-05-10 | 2 | Confirm UI works as expected
Product Owner | Prepare project documentation | Not Started | Medium | 2025-05-11 | 2025-05-12 | 2 | Write comprehensive project documentation
Product Owner | Final evaluation and system deployment preparation | Not Started | High | 2025-05-13 | 2025-05-14 | 2 | Prepare system for final deployment
16
BACKLOG
As a user, I want to securely complete my parking payment via a trusted payment gateway so that my transaction is processed safely and I receive immediate confirmation, and I want the system interface to be fully responsive and intuitive so that I enjoy a seamless experience across all devices, and I want to access a user-friendly dashboard to monitor my parking activities and manage my account with ease.
STATUS: Not Started
As an admin, I want to access a dashboard that lets me manage parking slots, transactions, and user registrations, so that I can efficiently oversee parking operations.
STATUS: Not Started
Dev
Dev
As a developer and product owner, I want to implement user authorization and role-based access control so that users interact with the system securely according to their roles, establish an error logging and alert system so that issues can be detected and resolved promptly, perform unit, integration, and UI testing to ensure system stability and quality, and prepare project documentation along with final evaluations so that the parking automation system is ready for deployment and further enhancement.
STATUS: Not Started
PO
Dev

## KeyDropdowns
KEY DROPDOWNS - DO NOT DELETE
CATEGORY KEY | PRIORITY KEY | STATUS KEY
Research | High | In Progress
Feature | Medium | Ready to Start
Content | Low | Complete
Task |  | On Hold
Update |  | Testing
Not Started

## Templates
TEMPLATES
ASSIGNED TO | KANBAN CARDS
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
Details of Task to Be Completed
STATUS: Note Status Here
POINTS: 0
Details of Task to Be Completed
STATUS: Note Status Here
POINTS: 0
Details of Task to Be Completed
STATUS: Note Status Here
POINTS: 0
Details of Task to Be Completed
STATUS: Note Status Here
POINTS: 0
Details of Task to Be Completed
STATUS: Note Status Here
POINTS: 0
Details of Task to Be Completed
STATUS: Note Status Here
POINTS: 0